## Sheet1
Sprint 1 | Week 1 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 2 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 3 | Monday | Tuesday | Wednesday | Thursday | Friday |  | Week 4 | Monday | Tuesday | End of Sprint 1
Code the UI | 9 |  | 2 |  | 2 | 1 | 4 |  | 2 |  | 1.5 |  | 0.5 |  |  |  | 0.5 |  |  | 0
Create Pokemon Class | 5 |  | 3 |  | 1 |  | 1 |  | 1 |  |  |  | 0 | [6 empty] | 0
Created Pokedex class | 3 |  | 2 |  |  |  | 1 | [5 empty] | 1 |  | 1 |  |  |  |  | 0
Make Unit Tests | 2 | [5 empty] | 2 |  | 0.5 |  |  |  | 1.5 | 1.5 | [5 empty] | 0
Write Comparable Classes | 2 | [5 empty] | 2 | [5 empty] | 2 |  | 2 |  |  |  |  | 0
Add Pokemon | 2 | [5 empty] | 2 | [5 empty] | 2 | [6 empty] | 2 | 2
Totals: | 23 | [5 empty] | 12 | [5 empty] | 7 | [6 empty] | 2 |  |  | 0
Sprint 2 | Week 5 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 6 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 7 | Monday | Tuesday | Wednesday | Thursday | Friday |  | Week 8 | Monday | Tuesday | End of Sprint 2
Add Close button functionality | 2 | [5 empty] | 2 | [5 empty] | 2 | [6 empty] | 2 | 2 |  | 0
Add caught/seen tags | 2 | [5 empty] | 2 | [5 empty] | 2 | [6 empty] | 2 | 2 |  | 0
Add labels to UI | 4 |  |  |  | 1 |  | 3 | 3 |  |  |  |  | 0 | [6 empty] | 0 |  |  | 0
Add the ability to add pokemon | 6 | [5 empty] | 6 |  |  |  |  | 1 | 5 | [6 empty] | 5 | 5 |  | 0
Add UI elements related to adding pokemon | 4 | [5 empty] | 4 | [5 empty] | 4 | [6 empty] | 4 | 4 |  | 0
Add local database functionality | 5 | [5 empty] | 5 | 2 |  |  |  | 2 | 2 |  |  |  |  | 1 |  | 1 | 1 |  | 0
Add remaining pokemon data to the UI | 3 | [5 empty] | 3 |  |  |  | 3 |  | 0 | [6 empty] | 0 |  |  | 0
Add remaining sorts | 3 | [5 empty] | 3 | [5 empty] | 3 | [6 empty] | 3 | 3 |  | 0
Totals: | 29 | [5 empty] | 28 | [5 empty] | 18 | [6 empty] | 17 |  |  | 0
Sprint 3 | Week 9 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 10 | Monday | Tuesday | Wednesday | Thursday | Friday | Week 11 | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | End of Sprint 3
Add Evolution information | 4 | [5 empty] | 4 | [5 empty] | 4 |  | 2 |  | 2 |  |  | 0
Add Move Lists | 6 |  | 1 |  |  |  | 5 |  |  | 2 | 2 |  | 1 |  |  |  | 1 |  |  | 0
Add remaining sort types | 3 |  |  |  | 1 |  | 2 |  | 1 |  |  |  | 1 | 1 | [5 empty] | 0
Ensure 100% code coverage | 5 | 0.5 |  |  | 0.5 |  | 4 | 1 |  | 1 |  |  | 4.5 |  | 1 |  | 1 |  | 2.5 | 0
Fix existing bugs | 2 | 0.5 |  |  |  |  | 1.5 |  |  |  | 1 |  | 1.5 |  |  | 0.5 |  |  | 1 | 0
Add remaining functionality to client/server connection | 6 |  |  | 2 |  |  | 4 |  | 2 |  | 2 |  | 1.5 | [5 empty] | 1.5 | 0
Logger | 0 | [5 empty] | 0 | [5 empty] | 1 |  |  |  | 1 |  |  | 0
Totals: | 26 | [5 empty] | 20.5 | [5 empty] | 14.5 | [6 empty] | 0